## Orders
APM NO | PO Date | PO Number | Part Number | Part Photo | Qty | Dispatch Date | Specification | Risk | RM Size | Action Qty | RM Status | Process | Tools & Accessories | Special Process & Instruments | Inserts | Enquiry | Program Status | Planning | Machining Status | Review | Deviation | Customer | Completed Status | RMA Status | Is Aerospace Order | Cost
APM-26041 | 2026-06-02 | PO-45021 | PN-1042 | assets/parts/pn-1042.png | 9 | 2026-06-20 | OD 25.00 ±0.01 mm, length 140 mm, Ra 0.8 | High | Ø32 × 180 mm bar | 8 | Ordered 02 Jun 2026; Received 10 Jun 2026 | CNC Turning, Grinding | Soft jaws, steady rest | CMM final inspection | DNMG 150608 |  | Completed | Turning in-house completed | All stages complete |  |  | Apex Aerospace | Completed | No | Yes | 225
APM-26042 | 2026-06-06 | PO-45021 | PN-1188 | assets/parts/pn-1188.png | 12 | 2026-10-13 | Bore 42 H7, face squareness 0.02 mm | Medium | 80 × 80 × 50 mm block | 13 | Not ordered | CNC Milling, Boring | Machine vice, boring head | Bore gauge | CCMT 09T304 |  | Incomplete | Milling out | Not started | First article accepted |  | Northline Auto | Not started | No | No | 300
APM-26043 | 2026-06-10 | PO-45022 | PN-2071 | assets/parts/pn-2071.png | 4 | 2026-06-28 | Hole pattern 2 × M8, thickness 12 mm | Low | 100 × 60 × 16 mm plate | 6 | Ordered 10 Jun 2026; Received 18 Jun 2026 | CNC Milling, Drilling & Tapping | Hold-down clamps |  | APMT 1135 | Confirm datum B on revision D | Completed | Milling in-house completed | All stages complete |  |  | Harbor Medical | Completed | No | No | 100
APM-26044 | 2026-06-14 | PO-45022 | PN-2210 | assets/parts/pn-2210.png | 20 | 2026-10-15 | PCD 70 mm, 4 × Ø6.6 through, face Ra 1.6 | High | Ø90 × 22 mm blank | 20 | Ordered 14 Jun 2026; Received 23 Jun 2026 | CNC Turning, CNC Milling | Soft jaws, drill jig | Anodise after machining | WNMG 080408 |  | Incomplete | In-house | Facing complete; finish pass in progress | Customer rejected the lot; remanufacture required |  | Vertex Robotics | In progress | Yes | Yes | 500
APM-26045 | 2026-06-18 | PO-45023 | PN-3055 | assets/parts/pn-3055.png | 16 | 2026-09-18 | Module 1.5, 30 teeth, bore 20 H7 | Medium | Ø55 × 20 mm blank | 17 | Not ordered | CNC Turning, Gear hobbing | Expanding mandrel | Gear profile check | VBMT 160404 | Customer asked for a material cert with the shipment | Incomplete | Turning in-house | Not started |  |  | Summit Energy | Not started | No | No | 400
APM-26046 | 2026-06-22 | PO-45023 | PN-3180 | assets/parts/pn-3180.png | 10 | 2026-07-10 | 4 ports 1/8 BSP, cross-hole burr free | Low | 70 × 40 × 30 mm block | 12 | Ordered 22 Jun 2026; Received 30 Jun 2026 | CNC Milling, Drilling | Side clamps, spot drill | Pressure test 10 bar | APMT 1135 |  | Completed | Milling out completed | All stages complete | Tool wear noted on the last two pieces |  | Precision Rail | Completed | No | No | 250
APM-26047 | 2026-06-26 | PO-45024 | PN-4022 | assets/parts/pn-4022.png | 24 | 2026-09-27 | OD 18 h6, ID 12 H7, length 25 mm | High | Ø22 × 40 mm bar | 24 | Ordered 26 Jun 2026; awaiting receipt | CNC Turning | Collet chuck |  | DCMT 11T304 |  | Incomplete | Turning in-house | Internal reject: bore out of tolerance |  | Bore +0.04 mm on 3 pieces | Apex Aerospace | In progress | No | Yes | 600
APM-26048 | 2026-06-30 | PO-45024 | PN-4156 | assets/parts/pn-4156.png | 6 | 2026-10-19 | 120 × 80 × 8 mm, 4 × Ø5.5 holes | Medium | 130 × 90 × 10 mm plate | 7 | Not ordered | CNC Milling, Deburr | Vacuum fixture |  | APKT 1604 |  | Incomplete | Milling in-house | Not started | First article accepted |  | Northline Auto | Not started | No | No | 150
APM-26049 | 2026-07-04 | PO-45025 | PN-5008 | assets/parts/pn-5008.png | 8 | 2026-07-22 | Ø8 m6 × 30 mm, both ends chamfered | Low | Ø10 × 45 mm bar | 10 | Ordered 04 Jul 2026; Received 12 Jul 2026 | CNC Turning | Guide bush |  | DCGT 11T302 | Confirm datum B on revision D | Completed | Turning in-house completed | All stages complete |  |  | Harbor Medical | Completed | No | No | 200
APM-26050 | 2026-07-08 | PO-45025 | PN-5124 | assets/parts/pn-5124.png | 12 | 2026-10-21 | Seat angle 30°, stem bore 6 H7 | High | Ø28 × 50 mm bar | 12 | Ordered 08 Jul 2026; Received 17 Jul 2026 | CNC Turning, CNC Milling | Live centre, small vice | Seat blue check | VBMT 160404 |  | Incomplete | Out | Finish pass complete; deburr pending | Hold shipment until the CMM report is attached | OD +0.02 mm on 1 piece, accepted by review | Vertex Robotics | In progress | No | Yes | 300
APM-26051 | 2026-07-12 | PO-45026 | PN-1042 | assets/parts/pn-1042.png | 4 | 2026-09-30 | OD 25.00 ±0.01 mm, length 140 mm, Ra 0.8 | Medium | Ø32 × 180 mm bar | 5 | Ordered 12 Jul 2026; Received 18 Jul 2026 | CNC Turning, Grinding | Soft jaws, steady rest | CMM final inspection | DNMG 150608 | Customer asked for a material cert with the shipment | Completed | Turning in-house | Facing complete; finish pass in progress | Customer rejected the lot; remanufacture required |  | Summit Energy | In progress | Yes | No | 100
APM-26052 | 2026-07-16 | PO-45026 | PN-1188 | assets/parts/pn-1188.png | 20 | 2026-08-03 | Bore 42 H7, face squareness 0.02 mm | Low | 80 × 80 × 50 mm block | 22 | Ordered 16 Jul 2026; Received 24 Jul 2026 | CNC Milling, Boring | Machine vice, boring head | Bore gauge | CCMT 09T304 |  | Completed | Milling in-house completed | All stages complete | Tool wear noted on the last two pieces |  | Precision Rail | Completed | No | No | 500
APM-26053 | 2026-07-20 | PO-45027 | PN-2071 | assets/parts/pn-2071.png | 16 | 2026-09-24 | Hole pattern 2 × M8, thickness 12 mm | High | 100 × 60 × 16 mm plate | 16 | Ordered 20 Jul 2026; awaiting receipt | CNC Milling, Drilling & Tapping | Hold-down clamps |  | APMT 1135 |  | Incomplete | Milling in-house | Facing complete; finish pass in progress |  |  | Apex Aerospace | In progress | No | Yes | 400
APM-26054 | 2026-07-24 | PO-45027 | PN-2210 | assets/parts/pn-2210.png | 10 | 2026-08-11 | PCD 70 mm, 4 × Ø6.6 through, face Ra 1.6 | Medium | Ø90 × 22 mm blank | 11 | Ordered 24 Jul 2026; Received 01 Aug 2026 | CNC Turning, CNC Milling | Soft jaws, drill jig | Anodise after machining | WNMG 080408 |  | Completed | Out completed | All stages complete | First article accepted |  | Northline Auto | Completed | No | No | 250
APM-26055 | 2026-07-28 | PO-45028 | PN-3055 | assets/parts/pn-3055.png | 24 | 2026-09-18 | Module 1.5, 30 teeth, bore 20 H7 | High | Ø55 × 20 mm blank | 26 | Ordered 28 Jul 2026; awaiting receipt | CNC Turning, Gear hobbing | Expanding mandrel | Gear profile check | VBMT 160404 | Confirm datum B on revision D | Incomplete | Turning in-house | Internal reject: sealing face tool mark |  | Tool mark across the sealing face | Harbor Medical | In progress | No | No | 600
APM-26056 | 2026-08-01 | PO-45028 | PN-3180 | assets/parts/pn-3180.png | 6 | 2026-10-15 | 4 ports 1/8 BSP, cross-hole burr free | High | 70 × 40 × 30 mm block | 6 | Ordered 01 Aug 2026; Received 07 Aug 2026 | CNC Milling, Drilling | Side clamps, spot drill | Pressure test 10 bar | APMT 1135 |  | Completed | Milling in-house | Facing complete; finish pass in progress | Hold shipment until the CMM report is attached |  | Vertex Robotics | In progress | No | Yes | 150
APM-26057 | 2026-08-05 | PO-45029 | PN-4022 | assets/parts/pn-4022.png | 8 | 2026-09-27 | OD 18 h6, ID 12 H7, length 25 mm | Medium | Ø22 × 40 mm bar | 9 | Ordered 05 Aug 2026; awaiting receipt | CNC Turning | Collet chuck |  | DCMT 11T304 | Customer asked for a material cert with the shipment | Incomplete | Turning in-house | Facing complete; finish pass in progress | Customer rejected the lot; remanufacture required |  | Summit Energy | In progress | Yes | No | 200
APM-26058 | 2026-08-09 | PO-45029 | PN-4156 | assets/parts/pn-4156.png | 12 | 2026-08-27 | 120 × 80 × 8 mm, 4 × Ø5.5 holes | Low | 130 × 90 × 10 mm plate | 14 | Ordered 09 Aug 2026; Received 17 Aug 2026 | CNC Milling, Deburr | Vacuum fixture |  | APKT 1604 |  | Completed | Milling out completed | All stages complete | Tool wear noted on the last two pieces |  | Precision Rail | Completed | No | No | 300
APM-26059 | 2026-08-13 | PO-45030 | PN-5008 | assets/parts/pn-5008.png | 4 | 2026-09-21 | Ø8 m6 × 30 mm, both ends chamfered | High | Ø10 × 45 mm bar | 4 | Ordered 13 Aug 2026; awaiting receipt | CNC Turning | Guide bush |  | DCGT 11T302 |  | Incomplete | Turning in-house | Facing complete; finish pass in progress |  |  | Apex Aerospace | In progress | No | Yes | 100
APM-26060 | 2026-08-17 | PO-45030 | PN-5124 | assets/parts/pn-5124.png | 20 | 2026-09-04 | Seat angle 30°, stem bore 6 H7 | Medium | Ø28 × 50 mm bar | 21 | Ordered 17 Aug 2026; Received 25 Aug 2026 | CNC Turning, CNC Milling | Live centre, small vice | Seat blue check | VBMT 160404 |  | Completed | In-house completed | All stages complete | First article accepted |  | Northline Auto | Completed | No | No | 500
APM-26061 | 2026-08-21 | PO-45031 | PN-1042 | assets/parts/pn-1042.png | 16 | 2026-09-30 | OD 25.00 ±0.01 mm, length 140 mm, Ra 0.8 | High | Ø32 × 180 mm bar | 18 | Ordered 21 Aug 2026; Received 27 Aug 2026 | CNC Turning, Grinding | Soft jaws, steady rest | CMM final inspection | DNMG 150608 | Confirm datum B on revision D | Completed | Turning in-house | Internal reject: sealing face tool mark |  | Tool mark across the sealing face | Harbor Medical | In progress | No | No | 400
APM-26062 | 2026-08-25 | PO-45031 | PN-1188 | assets/parts/pn-1188.png | 10 | 2026-10-21 | Bore 42 H7, face squareness 0.02 mm | High | 80 × 80 × 50 mm block | 10 | Ordered 25 Aug 2026; Received 03 Sep 2026 | CNC Milling, Boring | Machine vice, boring head | Bore gauge | CCMT 09T304 |  | Incomplete | Milling out | Facing complete; finish pass in progress | Hold shipment until the CMM report is attached |  | Vertex Robotics | In progress | No | Yes | 250
APM-26063 | 2026-08-29 | PO-45032 | PN-2071 | assets/parts/pn-2071.png | 24 | 2026-09-24 | Hole pattern 2 × M8, thickness 12 mm | Medium | 100 × 60 × 16 mm plate | 25 | Ordered 29 Aug 2026; awaiting receipt | CNC Milling, Drilling & Tapping | Hold-down clamps |  | APMT 1135 | Customer asked for a material cert with the shipment | Incomplete | Milling in-house | Facing complete; finish pass in progress |  |  | Summit Energy | On hold | No | No | 600
APM-26064 | 2026-09-02 | PO-45032 | PN-2210 | assets/parts/pn-2210.png | 6 | 2026-10-23 | PCD 70 mm, 4 × Ø6.6 through, face Ra 1.6 | Low | Ø90 × 22 mm blank | 8 | Ordered 02 Sep 2026; Received 11 Sep 2026 | CNC Turning, CNC Milling | Soft jaws, drill jig | Anodise after machining | WNMG 080408 |  | Incomplete | In-house | Facing complete; finish pass in progress | Tool wear noted on the last two pieces |  | Precision Rail | On hold | No | No | 150